**Event Wrap-up Report**

* **Summary**: The CairoCoders Hackathon 2024 successfully brought together 150 participants, with 20 mentors and 10 sponsors. Key workshops on AI, blockchain, and web development were conducted. Despite Wi-Fi issues requiring a $500 expense, the event was well-received.
* **Metrics**: 150 participants, $15,500 spent, 100 feedback responses collected.
* **Completed Tasks**: Vendor payments, venue cleanup, post-event surveys distributed.

**Sprint Retrospective Summary**

* **What Went Well**:
  + High participant turnout and engagement.
  + Strong support from sponsors and mentors.
* **What Didn’t Go Well**:
  + Wi-Fi disruption during the event.
* **Areas for Improvement**:
  + Arrange backup internet solutions.
  + Enhance communication with venue management.