**Sprint Planning**

**Sprint Plan**

**Sprint 1: Initial Setup & Logistics**

* **Goal**: Secure foundational elements for the hackathon.

|  |  |  |
| --- | --- | --- |
| **Task** | **Owner** | **Deadline** |
| Secure event venue | Logistics Team | Week 1 |
| Confirm Wi-Fi setup | Logistics Team | Week 1 |
| Confirm sponsorships | Sponsorship Team | Week 2 |

**Sprint 2: Promotion & Workshops**

* **Goal**: Finalize event promotion and workshop planning.

|  |  |  |
| --- | --- | --- |
| **Task** | **Owner** | **Deadline** |
| Social media campaign | Marketing Team | Week 3 |
| Finalize workshop topics | Workshop Team | Week 3 |
| Open registration | Registration Team | Week 4 |