## Sheet1
Task-ID | Task | Sub-tasks | Assigned Team Member | Priority | Deadline
T1 | Venue Setup | Secure venue, Arrange Wi-Fi, Organize equipment | Logistics Team | High | Week1
T2 | Sponsor & Mentor Coordination | Confirm sponsors, Assign mentors, Finalize judges | Sponsorship Team | High | Week2
T3 | Participant Registration | Open registration, Promote event, Manage inquiries | Registration Team | High | Week3
T4 | Workshop & Content Planning | Plan workshops, Confirm speakers, Prepare materials | Content Team | Medium | Week3
T5 | Event-Day Logistics | Catering setup, Technical support, On-site management | Operations Team | High | Week4 -Event days
T6 | Post-Event Wrap-Up | Survey participants, Process payments, Venue cleanup | Finance & Feedback Team | Medium | Week4